## WBS with Gantt Chart
WORK BREAKDOWN STRUCTURE WITH GANTT CHART
PROJECT TITLE |  | ELEMENT ARENA |  |  |  |  | INSTRUCTOR NAME | [8 empty] | ROY VINCENT
PROJECT MANAGER |  | GROUP #2 |  |  |  |  | DATE | [8 empty] | 2018-08-21
[7 empty] | phase one |  |  | & two |  | phase three & four
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2
[7 empty] | M | T | W | TH | F | S | M | T | W | TH
1 | Requirements
1.1 | Discussion of the instructor | Abundo , Brent | 2018-08-21 | 2018-08-21 | 1 | 100% | bar: WEEK 1 T
1.1.1 | Requirements | Punay , Jenelyn | 2018-08-21 | 2018-08-21 | 1 | 100% | bar: WEEK 1 T
1.2 | Gant Chart Finalizing | Janel Mae V Hortelano | 2018-08-21 | 2018-08-21 | 1 | 100% | bar: WEEK 1 T
1.3 | Finalizing the diagram | Punay , Jenelyn | 2018-08-21 | 2018-08-21 | 1 | 100% | bar: WEEK 1 T
1.4 | Checking | Janel Mae V Hortelano | 2018-08-21 | 2018-08-21 | 1 | 100% | bar: WEEK 1 T
2 | Analysis & Design
2.1 | UI Design | Abundo , Brent | 2018-08-21 | 2018-08-25 | 5 | 100% | bar: WEEK 1 T to WEEK 2 S
2.2 | Design Diagram | Dequina , Shiela | 2018-08-21 | 2018-08-25 | 5 | 100% | bar: WEEK 1 T to WEEK 2 S
2.3 | Astah | Geraldo , Rodnie | 2018-08-21 | 2018-08-25 | 5 | 100% | bar: WEEK 1 T to WEEK 2 S
2.4 | Finalizing | Caballero , Clyde | 2018-08-21 | 2018-08-25 | 5 | 100% | bar: WEEK 1 T to WEEK 2 S
3 | Project Implementation
3.1 | Input Player Name | Caballero , Clyde | 2018-08-21 | 2018-08-29 | 8 | 100% | bar: WEEK 1 T to WEEK 2 W
3.2 | Submit Botton | Geraldo , Rodnie | 2018-08-21 | 2018-08-29 | 8 | 100% | bar: WEEK 1 T to WEEK 2 W
3.3.1 | Change Botton | Abundo , Brent | 2018-08-21 | 2018-08-29 | 8 | 100% | bar: WEEK 1 T to WEEK 2 W
3.4 | Story Mode Botton | Abundo , Brent | 2018-08-21 | 2018-08-29 | 8 | 100% | bar: WEEK 1 T to WEEK 2 W
3.5 | Player Vs. Player | Abundo , Brent | 2018-08-21 | 2018-08-29 | 8 | 100% | bar: WEEK 1 T to WEEK 2 W
3.6 | Show Statistics | Abundo , Brent | 2018-08-21 | 2018-08-29 | 8 | 100% | bar: WEEK 1 T to WEEK 2 W
4 | Testing and Deployment
4.1 | Debugging | Punay , Jenelyn | 2018-08-24 | 2018-08-29 | 5 | 100% | bar: WEEK 1 F to WEEK 2 W
4.2 | First Testing | Janel Mae V Hortelano | 2018-08-27 | 2018-08-29 | 3 | 100% | bar: WEEK 2 M to WEEK 2 W
4.3 | Final Debugging | Abundo , Brent | 2018-08-28 | 2018-08-29 | 2 | 100% | bar: WEEK 2 T to WEEK 2 W
4.4 | Final Testing | all members | 2018-08-29 | 2018-08-29 | 1 | 100% | bar: WEEK 2 W
CLICK HERE TO CREATE WBS TEMPLATES WITH GANTT CHART IN SMARTSHEET

## WBS with Gantt Chart BLANK (hidden)
WORK BREAKDOWN STRUCTURE WITH GANTT CHART
PROJECT TITLE | [6 empty] | COMPANY NAME
PROJECT MANAGER | [6 empty] | DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1
1.1 | [5 empty] | 20%
100%
90%
40%
70%
60%
50%
100%
30%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
CLICK HERE TO CREATE WBS OUTLINE AND DIAGRAM TEMPLATES IN SMARTSHEET